## 2026 Scrum Board
Task ID | Epic | Story ID | Story Title | Category | Task | Student | Sprint | Priority | Status | Details
SCRUM-001 | Case Register | CASE_01 | Case Entry | Backend | Case creation API |  | Focus Learning | 1 | To Do | See Backlog row 2
SCRUM-002 | Case Register | CASE_01 | Case Entry | Backend | Airport code lookup integration |  | Focus Learning | 1 | To Do | See Backlog row 2
SCRUM-003 | Case Register | CASE_01 | Case Entry | Backend | Connecting-flight logic |  | Focus Learning | 1 | To Do | See Backlog row 2
SCRUM-004 | Case Register | CASE_01 | Case Entry | Backend | Problem-flight validation |  | Focus Learning | 1 | To Do | See Backlog row 2
SCRUM-005 | Case Register | CASE_01 | Case Entry | Backend | File upload validation |  | Focus Learning | 1 | To Do | See Backlog row 2
SCRUM-006 | Case Register | CASE_01 | Case Entry | Backend | GDPR consent enforcement |  | Focus Learning | 1 | To Do | See Backlog row 2
SCRUM-007 | Case Register | CASE_01 | Case Entry | Backend | Case status workflow |  | Focus Learning | 1 | To Do | See Backlog row 2
SCRUM-008 | Case Register | CASE_01 | Case Entry | Frontend | Case entry form |  | Focus Learning | 1 | To Do | See Backlog row 2
SCRUM-009 | Case Register | CASE_01 | Case Entry | Frontend | Passenger details section |  | Focus Learning | 1 | To Do | See Backlog row 2
SCRUM-010 | Case Register | CASE_01 | Case Entry | Frontend | Flight details section |  | Focus Learning | 1 | To Do | See Backlog row 2
SCRUM-011 | Case Register | CASE_01 | Case Entry | Frontend | Connecting flights UI |  | Focus Learning | 1 | To Do | See Backlog row 2
SCRUM-012 | Case Register | CASE_01 | Case Entry | Frontend | Document upload UI |  | Focus Learning | 1 | To Do | See Backlog row 2
SCRUM-013 | Case Register | CASE_01 | Case Entry | Frontend | GDPR checkbox UI |  | Focus Learning | 1 | To Do | See Backlog row 2
SCRUM-014 | Case Register | CASE_01 | Case Entry | Frontend | Required-field validation |  | Focus Learning | 1 | To Do | See Backlog row 2
SCRUM-015 | Case Register | CASE_01 | Case Entry | Database | Case table/model |  | Focus Learning | 1 | To Do | See Backlog row 2
SCRUM-016 | Case Register | CASE_01 | Case Entry | Database | Passenger data fields |  | Focus Learning | 1 | To Do | See Backlog row 2
SCRUM-017 | Case Register | CASE_01 | Case Entry | Database | Flight/connection records |  | Focus Learning | 1 | To Do | See Backlog row 2
SCRUM-018 | Case Register | CASE_01 | Case Entry | Database | Uploaded document metadata |  | Focus Learning | 1 | To Do | See Backlog row 2
SCRUM-019 | Case Register | CASE_01 | Case Entry | Database | GDPR consent fields |  | Focus Learning | 1 | To Do | See Backlog row 2
SCRUM-020 | Case Register | CASE_01 | Case Entry | Database | Case status field |  | Focus Learning | 1 | To Do | See Backlog row 2
SCRUM-021 | Case Register | CASE_02 | Calculate Compensation Level | Backend | Integrate airport distance API |  | Focus Learning | 1 | To Do | See Backlog row 3
SCRUM-022 | Case Register | CASE_02 | Calculate Compensation Level | Backend | Calculate orthodromic distance |  | Focus Learning | 1 | To Do | See Backlog row 3
SCRUM-023 | Case Register | CASE_02 | Calculate Compensation Level | Backend | Apply compensation thresholds |  | Focus Learning | 1 | To Do | See Backlog row 3
SCRUM-024 | Case Register | CASE_02 | Calculate Compensation Level | Backend | Persist calculated compensation result |  | Focus Learning | 1 | To Do | See Backlog row 3
SCRUM-025 | Case Register | CASE_02 | Calculate Compensation Level | Frontend | Display calculated distance |  | Focus Learning | 1 | To Do | See Backlog row 3
SCRUM-026 | Case Register | CASE_02 | Calculate Compensation Level | Frontend | Display compensation amount |  | Focus Learning | 1 | To Do | See Backlog row 3
SCRUM-027 | Case Register | CASE_02 | Calculate Compensation Level | Frontend | Trigger recalculation when airports change |  | Focus Learning | 1 | To Do | See Backlog row 3
SCRUM-028 | Case Register | CASE_02 | Calculate Compensation Level | Database | Store distance result |  | Focus Learning | 1 | To Do | See Backlog row 3
SCRUM-029 | Case Register | CASE_02 | Calculate Compensation Level | Database | Store compensation amount |  | Focus Learning | 1 | To Do | See Backlog row 3
SCRUM-030 | Case Register | CASE_02 | Calculate Compensation Level | Database | Link calculation data to case record |  | Focus Learning | 1 | To Do | See Backlog row 3
SCRUM-031 | Case Register | CASE_03 | Collect Disruption Motives | Backend | Process disruption type selection |  | Focus Learning | 1 | To Do | See Backlog row 4
SCRUM-032 | Case Register | CASE_03 | Collect Disruption Motives | Backend | Validate disruption presence before submission |  | Focus Learning | 1 | To Do | See Backlog row 4
SCRUM-033 | Case Register | CASE_03 | Collect Disruption Motives | Backend | Store disruption answers without strict answer validation |  | Focus Learning | 1 | To Do | See Backlog row 4
SCRUM-034 | Case Register | CASE_03 | Collect Disruption Motives | Frontend | Build disruption type dropdown |  | Focus Learning | 1 | To Do | See Backlog row 4
SCRUM-035 | Case Register | CASE_03 | Collect Disruption Motives | Frontend | Show conditional fields by disruption type |  | Focus Learning | 1 | To Do | See Backlog row 4
SCRUM-036 | Case Register | CASE_03 | Collect Disruption Motives | Frontend | Add incident description text box |  | Focus Learning | 1 | To Do | See Backlog row 4
SCRUM-037 | Case Register | CASE_03 | Collect Disruption Motives | Frontend | Enforce disruption section completion |  | Focus Learning | 1 | To Do | See Backlog row 4
SCRUM-038 | Case Register | CASE_03 | Collect Disruption Motives | Database | Store disruption type |  | Focus Learning | 1 | To Do | See Backlog row 4
SCRUM-039 | Case Register | CASE_03 | Collect Disruption Motives | Database | Store cancellation, delay, and denied boarding answers |  | Focus Learning | 1 | To Do | See Backlog row 4
SCRUM-040 | Case Register | CASE_03 | Collect Disruption Motives | Database | Store airline motive details |  | Focus Learning | 1 | To Do | See Backlog row 4
SCRUM-041 | Case Register | CASE_03 | Collect Disruption Motives | Database | Store incident description |  | Focus Learning | 1 | To Do | See Backlog row 4
SCRUM-042 | Case Eligibility Verification | ELIGIBILITY_01 | Eligibility Determination | Backend | Implement eligibility rules for cancellation |  | 1 | 1 | To Do | See Backlog row 5
SCRUM-043 | Case Eligibility Verification | ELIGIBILITY_01 | Eligibility Determination | Backend | Implement eligibility rules for delay |  | 1 | 1 | To Do | See Backlog row 5
SCRUM-044 | Case Eligibility Verification | ELIGIBILITY_01 | Eligibility Determination | Backend | Implement eligibility rules for denied boarding |  | 1 | 1 | To Do | See Backlog row 5
SCRUM-045 | Case Eligibility Verification | ELIGIBILITY_01 | Eligibility Determination | Backend | Set case status to VALID when eligible |  | 1 | 1 | To Do | See Backlog row 5
SCRUM-046 | Case Eligibility Verification | ELIGIBILITY_01 | Eligibility Determination | Frontend | Show eligibility result feedback |  | 1 | 1 | To Do | See Backlog row 5
SCRUM-047 | Case Eligibility Verification | ELIGIBILITY_01 | Eligibility Determination | Frontend | Prevent progression for ineligible cases |  | 1 | 1 | To Do | See Backlog row 5
SCRUM-048 | Case Eligibility Verification | ELIGIBILITY_01 | Eligibility Determination | Database | Store eligibility outcome |  | 1 | 1 | To Do | See Backlog row 5
SCRUM-049 | Case Eligibility Verification | ELIGIBILITY_01 | Eligibility Determination | Database | Store eligibility decision inputs |  | 1 | 1 | To Do | See Backlog row 5
SCRUM-050 | Case Eligibility Verification | ELIGIBILITY_01 | Eligibility Determination | Database | Update case status field |  | 1 | 1 | To Do | See Backlog row 5
SCRUM-051 | Case Eligibility Verification | ELIGIBILITY_02 | Confirmation of Eligibility | Backend | Enforce only eligible cases can be stored |  | 1 | 1 | To Do | See Backlog row 6
SCRUM-052 | Case Eligibility Verification | ELIGIBILITY_02 | Confirmation of Eligibility | Backend | Generate unique case ID |  | 1 | 1 | To Do | See Backlog row 6
SCRUM-053 | Case Eligibility Verification | ELIGIBILITY_02 | Confirmation of Eligibility | Backend | Trigger confirmation email |  | 1 | 1 | To Do | See Backlog row 6
SCRUM-054 | Case Eligibility Verification | ELIGIBILITY_02 | Confirmation of Eligibility | Frontend | Show eligible confirmation message |  | 1 | 1 | To Do | See Backlog row 6
SCRUM-055 | Case Eligibility Verification | ELIGIBILITY_02 | Confirmation of Eligibility | Frontend | Enable Submit button for eligible cases |  | 1 | 1 | To Do | See Backlog row 6
SCRUM-056 | Case Eligibility Verification | ELIGIBILITY_02 | Confirmation of Eligibility | Frontend | Show ineligible confirmation message |  | 1 | 1 | To Do | See Backlog row 6
SCRUM-057 | Case Eligibility Verification | ELIGIBILITY_02 | Confirmation of Eligibility | Frontend | Keep Submit button disabled for ineligible cases |  | 1 | 1 | To Do | See Backlog row 6
SCRUM-058 | Case Eligibility Verification | ELIGIBILITY_02 | Confirmation of Eligibility | Database | Store eligible case record |  | 1 | 1 | To Do | See Backlog row 6
SCRUM-059 | Case Eligibility Verification | ELIGIBILITY_02 | Confirmation of Eligibility | Database | Persist generated case ID |  | 1 | 1 | To Do | See Backlog row 6
SCRUM-060 | Case Register | CASE_05 | Create User Account | Backend | Create passenger user account after case data capture |  | Focus Learning | 1 | To Do | See Backlog row 7
SCRUM-061 | Case Register | CASE_05 | Create User Account | Backend | Generate initial password |  | Focus Learning | 1 | To Do | See Backlog row 7
SCRUM-062 | Case Register | CASE_05 | Create User Account | Backend | Send password email |  | Focus Learning | 1 | To Do | See Backlog row 7
SCRUM-063 | Case Register | CASE_05 | Create User Account | Backend | Enforce password change on first login |  | Focus Learning | 1 | To Do | See Backlog row 7
SCRUM-064 | Case Register | CASE_05 | Create User Account | Frontend | Support login with generated credentials |  | Focus Learning | 1 | To Do | See Backlog row 7
SCRUM-065 | Case Register | CASE_05 | Create User Account | Frontend | Prompt password change on first login |  | Focus Learning | 1 | To Do | See Backlog row 7
SCRUM-066 | Case Register | CASE_05 | Create User Account | Database | Store passenger user account |  | Focus Learning | 1 | To Do | See Backlog row 7
SCRUM-067 | Case Register | CASE_05 | Create User Account | Database | Store password reset/change-required flag |  | Focus Learning | 1 | To Do | See Backlog row 7
SCRUM-068 | Case Register | CASE_05 | Create User Account | Database | Link user account to passenger/case data |  | Focus Learning | 1 | To Do | See Backlog row 7
SCRUM-069 | Case Register | CASE_04 | Save Case | Backend | Create case with unique ID and date |  | Focus Learning | 1 | To Do | See Backlog row 8
SCRUM-070 | Case Register | CASE_04 | Save Case | Backend | Add empty colleague assignment field |  | Focus Learning | 1 | To Do | See Backlog row 8
SCRUM-071 | Case Register | CASE_04 | Save Case | Backend | Save passenger, flight, and disruption details transactionally |  | Focus Learning | 1 | To Do | See Backlog row 8
SCRUM-072 | Case Register | CASE_04 | Save Case | Backend | Handle database save failures without partial data |  | Focus Learning | 1 | To Do | See Backlog row 8
SCRUM-073 | Case Register | CASE_04 | Save Case | Frontend | Submit completed case data |  | Focus Learning | 1 | To Do | See Backlog row 8
SCRUM-074 | Case Register | CASE_04 | Save Case | Frontend | Show save success or error message |  | Focus Learning | 1 | To Do | See Backlog row 8
SCRUM-075 | Case Register | CASE_04 | Save Case | Database | Create cases table fields |  | Focus Learning | 1 | To Do | See Backlog row 8
SCRUM-076 | Case Register | CASE_04 | Save Case | Database | Create flights table fields |  | Focus Learning | 1 | To Do | See Backlog row 8
SCRUM-077 | Case Register | CASE_04 | Save Case | Database | Create passengers table fields |  | Focus Learning | 1 | To Do | See Backlog row 8
SCRUM-078 | Case Register | CASE_04 | Save Case | Database | Create disruptions table fields |  | Focus Learning | 1 | To Do | See Backlog row 8
SCRUM-079 | Case Register | CASE_04 | Save Case | Database | Add primary and foreign key constraints |  | Focus Learning | 1 | To Do | See Backlog row 8
SCRUM-080 | Case Completion and Documentation | CASE_COMPLETED_01 | Generate PDF with Case Details | Backend | Generate PDF contract after form submission |  | 1 | 1 | To Do | See Backlog row 9
SCRUM-081 | Case Completion and Documentation | CASE_COMPLETED_01 | Generate PDF with Case Details | Backend | Include case ID, date, passenger details, and reservation number |  | 1 | 1 | To Do | See Backlog row 9
SCRUM-082 | Case Completion and Documentation | CASE_COMPLETED_01 | Generate PDF with Case Details | Backend | Store generated PDF |  | 1 | 1 | To Do | See Backlog row 9
SCRUM-083 | Case Completion and Documentation | CASE_COMPLETED_01 | Generate PDF with Case Details | Backend | Provide PDF download endpoint |  | 1 | 1 | To Do | See Backlog row 9
SCRUM-084 | Case Completion and Documentation | CASE_COMPLETED_01 | Generate PDF with Case Details | Frontend | Trigger PDF generation on submission |  | 1 | 1 | To Do | See Backlog row 9
SCRUM-085 | Case Completion and Documentation | CASE_COMPLETED_01 | Generate PDF with Case Details | Frontend | Show PDF download link in confirmation |  | 1 | 1 | To Do | See Backlog row 9
SCRUM-086 | Case Completion and Documentation | CASE_COMPLETED_01 | Generate PDF with Case Details | Frontend | Make PDF accessible from entry page |  | 1 | 1 | To Do | See Backlog row 9
SCRUM-087 | Case Completion and Documentation | CASE_COMPLETED_01 | Generate PDF with Case Details | Database | Store PDF document metadata |  | 1 | 1 | To Do | See Backlog row 9
SCRUM-088 | Case Completion and Documentation | CASE_COMPLETED_01 | Generate PDF with Case Details | Database | Link PDF file to case record |  | 1 | 1 | To Do | See Backlog row 9
SCRUM-089 | Case Completion and Documentation | CASE_COMPLETED_02 | Send Email Notification | Backend | Send registration confirmation email |  | 2 | 3 | To Do | See Backlog row 10
SCRUM-090 | Case Completion and Documentation | CASE_COMPLETED_02 | Send Email Notification | Backend | Include case ID in email |  | 2 | 3 | To Do | See Backlog row 10
SCRUM-091 | Case Completion and Documentation | CASE_COMPLETED_02 | Send Email Notification | Backend | Attach generated PDF when available |  | 2 | 3 | To Do | See Backlog row 10
SCRUM-092 | Case Completion and Documentation | CASE_COMPLETED_02 | Send Email Notification | Frontend | Show email notification confirmation if needed |  | 2 | 3 | To Do | See Backlog row 10
SCRUM-093 | Case Completion and Documentation | CASE_COMPLETED_02 | Send Email Notification | Database | Store email notification status |  | 2 | 3 | To Do | See Backlog row 10
SCRUM-094 | Case Completion and Documentation | CASE_COMPLETED_02 | Send Email Notification | Database | Store sent timestamp and delivery metadata |  | 2 | 3 | To Do | See Backlog row 10
SCRUM-095 | Employee Operations | EMPLOYEE_03 | Case List | Backend | Provide case list API for colleagues |  | 1 | 1 | To Do | See Backlog row 11
SCRUM-096 | Employee Operations | EMPLOYEE_03 | Case List | Backend | Apply colleague authorization |  | 1 | 1 | To Do | See Backlog row 11
SCRUM-097 | Employee Operations | EMPLOYEE_03 | Case List | Backend | Include assigned colleague and status data |  | 1 | 1 | To Do | See Backlog row 11
SCRUM-098 | Employee Operations | EMPLOYEE_03 | Case List | Frontend | Build colleague case list view |  | 1 | 1 | To Do | See Backlog row 11
SCRUM-099 | Employee Operations | EMPLOYEE_03 | Case List | Frontend | Display case ID, dates, flight, passenger, status, and assignee |  | 1 | 1 | To Do | See Backlog row 11
SCRUM-100 | Employee Operations | EMPLOYEE_03 | Case List | Frontend | Add navigation to case details |  | 1 | 1 | To Do | See Backlog row 11
SCRUM-101 | Employee Operations | EMPLOYEE_03 | Case List | Database | Query cases with passenger, flight, status, and colleague assignment joins |  | 1 | 1 | To Do | See Backlog row 11
SCRUM-102 | Employee Operations | EMPLOYEE_01 | Create Cases | Backend | Reuse case creation flow for colleagues |  | 1 | 1 | To Do | See Backlog row 12
SCRUM-103 | Employee Operations | EMPLOYEE_01 | Create Cases | Backend | Validate passenger, flight, and disruption data |  | 1 | 1 | To Do | See Backlog row 12
SCRUM-104 | Employee Operations | EMPLOYEE_01 | Create Cases | Backend | Return creation confirmation |  | 1 | 1 | To Do | See Backlog row 12
SCRUM-105 | Employee Operations | EMPLOYEE_01 | Create Cases | Frontend | Enable colleague case entry form |  | 1 | 1 | To Do | See Backlog row 12
SCRUM-106 | Employee Operations | EMPLOYEE_01 | Create Cases | Frontend | Show successful creation toast/snackbar |  | 1 | 1 | To Do | See Backlog row 12
SCRUM-107 | Employee Operations | EMPLOYEE_01 | Create Cases | Database | Store colleague-created case records |  | 1 | 1 | To Do | See Backlog row 12
SCRUM-108 | Employee Operations | EMPLOYEE_01 | Create Cases | Database | Link created case to creator if needed |  | 1 | 1 | To Do | See Backlog row 12
SCRUM-109 | Employee Operations | EMPLOYEE_05 | Case Details | Backend | Provide detailed case API for colleagues |  | 1 | 1 | To Do | See Backlog row 13
SCRUM-110 | Employee Operations | EMPLOYEE_05 | Case Details | Backend | Load flight, passenger, documents, and comments |  | 1 | 1 | To Do | See Backlog row 13
SCRUM-111 | Employee Operations | EMPLOYEE_05 | Case Details | Backend | Enforce colleague access rules |  | 1 | 1 | To Do | See Backlog row 13
SCRUM-112 | Employee Operations | EMPLOYEE_05 | Case Details | Frontend | Make case ID link open detailed case view |  | 1 | 1 | To Do | See Backlog row 13
SCRUM-113 | Employee Operations | EMPLOYEE_05 | Case Details | Frontend | Display full flight, passenger, document, and comment sections |  | 1 | 1 | To Do | See Backlog row 13
SCRUM-114 | Employee Operations | EMPLOYEE_05 | Case Details | Database | Query related case detail tables |  | 1 | 1 | To Do | See Backlog row 13
SCRUM-115 | Employee Operations | EMPLOYEE_05 | Case Details | Database | Support document and comment history retrieval |  | 1 | 1 | To Do | See Backlog row 13
SCRUM-116 | Employee Operations | EMPLOYEE_02 | Comment on Cases | Backend | Add colleague comment API |  | 1 | 2 | To Do | See Backlog row 14
SCRUM-117 | Employee Operations | EMPLOYEE_02 | Comment on Cases | Backend | Validate comment length and author |  | 1 | 2 | To Do | See Backlog row 14
SCRUM-118 | Employee Operations | EMPLOYEE_02 | Comment on Cases | Backend | Timestamp saved comments |  | 1 | 2 | To Do | See Backlog row 14
SCRUM-119 | Employee Operations | EMPLOYEE_02 | Comment on Cases | Frontend | Add comment text area and button |  | 2 | 2 | To Do | See Backlog row 14
SCRUM-120 | Employee Operations | EMPLOYEE_02 | Comment on Cases | Frontend | Show comment list with author and timestamp |  | 2 | 2 | To Do | See Backlog row 14
SCRUM-121 | Employee Operations | EMPLOYEE_02 | Comment on Cases | Database | Store case comments |  | 2 | 2 | To Do | See Backlog row 14
SCRUM-122 | Employee Operations | EMPLOYEE_02 | Comment on Cases | Database | Link comments to case and user |  | 2 | 2 | To Do | See Backlog row 14
SCRUM-123 | Employee Operations | EMPLOYEE_04 | Attach and Download Documents for Cases and Flights | Backend | Implement colleague document upload and download |  | 2 | 2 | To Do | See Backlog row 15
SCRUM-124 | Employee Operations | EMPLOYEE_04 | Attach and Download Documents for Cases and Flights | Backend | Validate file type and 5 MB limit |  | 2 | 2 | To Do | See Backlog row 15
SCRUM-125 | Employee Operations | EMPLOYEE_04 | Attach and Download Documents for Cases and Flights | Backend | Return upload/download confirmations |  | 2 | 2 | To Do | See Backlog row 15
SCRUM-126 | Employee Operations | EMPLOYEE_04 | Attach and Download Documents for Cases and Flights | Frontend | Add upload and download controls |  | 2 | 2 | To Do | See Backlog row 15
SCRUM-127 | Employee Operations | EMPLOYEE_04 | Attach and Download Documents for Cases and Flights | Frontend | Show document list and toast/snackbar confirmation |  | 2 | 2 | To Do | See Backlog row 15
SCRUM-128 | Employee Operations | EMPLOYEE_04 | Attach and Download Documents for Cases and Flights | Database | Store document metadata |  | 2 | 2 | To Do | See Backlog row 15
SCRUM-129 | Employee Operations | EMPLOYEE_04 | Attach and Download Documents for Cases and Flights | Database | Link documents to cases or flights |  | 2 | 2 | To Do | See Backlog row 15
SCRUM-130 | Employee Operations | EMPLOYEE_06 | Assign Cases to Colleagues | Backend | Provide colleague list for assignment |  | 2 | 2 | To Do | See Backlog row 16
SCRUM-131 | Employee Operations | EMPLOYEE_06 | Assign Cases to Colleagues | Backend | Update case assignee |  | 2 | 2 | To Do | See Backlog row 16
SCRUM-132 | Employee Operations | EMPLOYEE_06 | Assign Cases to Colleagues | Backend | Validate assignment permissions |  | 2 | 2 | To Do | See Backlog row 16
SCRUM-133 | Employee Operations | EMPLOYEE_06 | Assign Cases to Colleagues | Frontend | Add colleague dropdown and Assign button |  | 2 | 2 | To Do | See Backlog row 16
SCRUM-134 | Employee Operations | EMPLOYEE_06 | Assign Cases to Colleagues | Frontend | Refresh assignee field after assignment |  | 2 | 2 | To Do | See Backlog row 16
SCRUM-135 | Employee Operations | EMPLOYEE_06 | Assign Cases to Colleagues | Database | Store colleague assignment on case |  | 2 | 2 | To Do | See Backlog row 16
SCRUM-136 | Employee Operations | EMPLOYEE_06 | Assign Cases to Colleagues | Database | Maintain user-to-case relationship |  | 2 | 2 | To Do | See Backlog row 16
SCRUM-137 | Employee Operations | EMPLOYEE_07 | Check Eligibility of Flight and Claim | Backend | Support manual eligibility status update |  | 2 | 2 | To Do | See Backlog row 17
SCRUM-138 | Employee Operations | EMPLOYEE_07 | Check Eligibility of Flight and Claim | Backend | Send rejection email for non-eligible cases |  | 2 | 2 | To Do | See Backlog row 17
SCRUM-139 | Employee Operations | EMPLOYEE_07 | Check Eligibility of Flight and Claim | Backend | Flag rejected case status |  | 2 | 2 | To Do | See Backlog row 17
SCRUM-140 | Employee Operations | EMPLOYEE_07 | Check Eligibility of Flight and Claim | Frontend | Add eligibility checkbox/control |  | 2 | 2 | To Do | See Backlog row 17
SCRUM-141 | Employee Operations | EMPLOYEE_07 | Check Eligibility of Flight and Claim | Frontend | Display current case eligibility state |  | 2 | 2 | To Do | See Backlog row 17
SCRUM-142 | Employee Operations | EMPLOYEE_07 | Check Eligibility of Flight and Claim | Frontend | Show update confirmation |  | 2 | 2 | To Do | See Backlog row 17
SCRUM-143 | Employee Operations | EMPLOYEE_07 | Check Eligibility of Flight and Claim | Database | Store manual eligibility decision |  | 2 | 2 | To Do | See Backlog row 17
SCRUM-144 | Employee Operations | EMPLOYEE_07 | Check Eligibility of Flight and Claim | Database | Update case status and audit fields |  | 2 | 2 | To Do | See Backlog row 17
SCRUM-145 | Employee Operations | EMPLOYEE_08 | Show PDF History | Backend | Provide generated PDF history API |  | 2 | 3 | To Do | See Backlog row 18
SCRUM-146 | Employee Operations | EMPLOYEE_08 | Show PDF History | Backend | Enforce colleague access to PDF history |  | 2 | 3 | To Do | See Backlog row 18
SCRUM-147 | Employee Operations | EMPLOYEE_08 | Show PDF History | Frontend | Build PDF history view |  | 2 | 3 | To Do | See Backlog row 18
SCRUM-148 | Employee Operations | EMPLOYEE_08 | Show PDF History | Frontend | Display ID, document name, passenger name, and case ID |  | 2 | 3 | To Do | See Backlog row 18
SCRUM-149 | Employee Operations | EMPLOYEE_08 | Show PDF History | Database | Query generated PDF metadata |  | 2 | 3 | To Do | See Backlog row 18
SCRUM-150 | Employee Operations | EMPLOYEE_08 | Show PDF History | Database | Link PDFs to cases and passengers |  | 2 | 3 | To Do | See Backlog row 18
SCRUM-151 | System Administration | ROLE_00 | User List | Backend | Provide admin user list API |  | 1 | 1 | To Do | See Backlog row 19
SCRUM-152 | System Administration | ROLE_00 | User List | Backend | Include assigned case counts |  | 1 | 1 | To Do | See Backlog row 19
SCRUM-153 | System Administration | ROLE_00 | User List | Backend | Enforce admin authorization |  | 1 | 1 | To Do | See Backlog row 19
SCRUM-154 | System Administration | ROLE_00 | User List | Frontend | Build user list view |  | 1 | 1 | To Do | See Backlog row 19
SCRUM-155 | System Administration | ROLE_00 | User List | Frontend | Display name, email, role, assigned cases, and actions |  | 1 | 1 | To Do | See Backlog row 19
SCRUM-156 | System Administration | ROLE_00 | User List | Database | Query users and assigned case counts |  | 1 | 1 | To Do | See Backlog row 19
SCRUM-157 | System Administration | ROLE_01 | Create User Accounts | Backend | Implement colleague account creation |  | 1 | 1 | To Do | See Backlog row 20
SCRUM-158 | System Administration | ROLE_01 | Create User Accounts | Backend | Validate new user data |  | 1 | 1 | To Do | See Backlog row 20
SCRUM-159 | System Administration | ROLE_01 | Create User Accounts | Backend | Return creation confirmation |  | 1 | 1 | To Do | See Backlog row 20
SCRUM-160 | System Administration | ROLE_01 | Create User Accounts | Frontend | Build new user form |  | 1 | 1 | To Do | See Backlog row 20
SCRUM-161 | System Administration | ROLE_01 | Create User Accounts | Frontend | Show successful creation confirmation |  | 1 | 1 | To Do | See Backlog row 20
SCRUM-162 | System Administration | ROLE_01 | Create User Accounts | Database | Store colleague user account |  | 1 | 1 | To Do | See Backlog row 20
SCRUM-163 | System Administration | ROLE_01 | Create User Accounts | Database | Store assigned role and credentials metadata |  | 1 | 1 | To Do | See Backlog row 20
SCRUM-164 | System Administration | ROLE_02 | Delete User Accounts | Backend | Implement user deletion endpoint |  | 2 | 2 | To Do | See Backlog row 21
SCRUM-165 | System Administration | ROLE_02 | Delete User Accounts | Backend | Validate deletion permissions and constraints |  | 2 | 2 | To Do | See Backlog row 21
SCRUM-166 | System Administration | ROLE_02 | Delete User Accounts | Backend | Return deletion confirmation |  | 2 | 2 | To Do | See Backlog row 21
SCRUM-167 | System Administration | ROLE_02 | Delete User Accounts | Frontend | Add delete action to user list |  | 2 | 2 | To Do | See Backlog row 21
SCRUM-168 | System Administration | ROLE_02 | Delete User Accounts | Frontend | Show deletion confirmation message |  | 2 | 2 | To Do | See Backlog row 21
SCRUM-169 | System Administration | ROLE_02 | Delete User Accounts | Database | Delete or deactivate user accounts |  | 2 | 2 | To Do | See Backlog row 21
SCRUM-170 | System Administration | ROLE_02 | Delete User Accounts | Database | Preserve referential integrity for linked cases |  | 2 | 2 | To Do | See Backlog row 21
SCRUM-171 | System Administration | ROLE_03 | Delete Cases | Backend | Implement case deletion endpoint |  | 1 | 1 | To Do | See Backlog row 22
SCRUM-172 | System Administration | ROLE_03 | Delete Cases | Backend | Validate admin permissions |  | 1 | 1 | To Do | See Backlog row 22
SCRUM-173 | System Administration | ROLE_03 | Delete Cases | Backend | Return deletion confirmation |  | 1 | 1 | To Do | See Backlog row 22
SCRUM-174 | System Administration | ROLE_03 | Delete Cases | Frontend | Add delete button to case list |  | 1 | 1 | To Do | See Backlog row 22
SCRUM-175 | System Administration | ROLE_03 | Delete Cases | Frontend | Show successful deletion confirmation |  | 1 | 1 | To Do | See Backlog row 22
SCRUM-176 | System Administration | ROLE_03 | Delete Cases | Database | Delete or archive case records |  | 1 | 1 | To Do | See Backlog row 22
SCRUM-177 | System Administration | ROLE_03 | Delete Cases | Database | Handle dependent flight, passenger, document, and comment data |  | 1 | 1 | To Do | See Backlog row 22
SCRUM-178 | System Administration | ROLE_04 | Admin Landing Page | Backend | Provide admin navigation metadata if needed |  | 2 | 3 | To Do | See Backlog row 23
SCRUM-179 | System Administration | ROLE_04 | Admin Landing Page | Backend | Enforce admin-only access |  | 2 | 3 | To Do | See Backlog row 23
SCRUM-180 | System Administration | ROLE_04 | Admin Landing Page | Frontend | Build admin landing page |  | 2 | 3 | To Do | See Backlog row 23
SCRUM-181 | System Administration | ROLE_04 | Admin Landing Page | Frontend | Add links to New User, User, Case, and System views |  | 2 | 3 | To Do | See Backlog row 23
SCRUM-182 | System Administration | ROLE_05 | Change System Options | Backend | Implement system options management |  | 2 | 3 | To Do | See Backlog row 24
SCRUM-183 | System Administration | ROLE_05 | Change System Options | Backend | Support email preset and PDF preset configuration |  | 2 | 3 | To Do | See Backlog row 24
SCRUM-184 | System Administration | ROLE_05 | Change System Options | Backend | Validate configuration changes |  | 2 | 3 | To Do | See Backlog row 24
SCRUM-185 | System Administration | ROLE_05 | Change System Options | Frontend | Build system options view |  | 2 | 3 | To Do | See Backlog row 24
SCRUM-186 | System Administration | ROLE_05 | Change System Options | Frontend | Add editable email and PDF preset fields |  | 2 | 3 | To Do | See Backlog row 24
SCRUM-187 | System Administration | ROLE_05 | Change System Options | Frontend | Show save confirmation |  | 2 | 3 | To Do | See Backlog row 24
SCRUM-188 | System Administration | ROLE_05 | Change System Options | Database | Store system option records |  | 2 | 3 | To Do | See Backlog row 24
SCRUM-189 | System Administration | ROLE_05 | Change System Options | Database | Persist email and PDF preset settings |  | 2 | 3 | To Do | See Backlog row 24
SCRUM-190 | Passenger Operations | PASSENEGER_02 | View Past Cases | Backend | Provide passenger case list API |  | 1 | 1 | To Do | See Backlog row 25
SCRUM-191 | Passenger Operations | PASSENEGER_02 | View Past Cases | Backend | Restrict results to logged-in passenger |  | 1 | 1 | To Do | See Backlog row 25
SCRUM-192 | Passenger Operations | PASSENEGER_02 | View Past Cases | Frontend | Build passenger past cases view |  | 1 | 1 | To Do | See Backlog row 25
SCRUM-193 | Passenger Operations | PASSENEGER_02 | View Past Cases | Frontend | Display ID, flight number, passenger name, status, and assignee |  | 1 | 1 | To Do | See Backlog row 25
SCRUM-194 | Passenger Operations | PASSENEGER_02 | View Past Cases | Database | Query cases linked to passenger account |  | 1 | 1 | To Do | See Backlog row 25
SCRUM-195 | Passenger Operations | PASSENEGER_01 | View Past Case Details | Backend | Provide passenger case details API |  | 1 | 1 | To Do | See Backlog row 26
SCRUM-196 | Passenger Operations | PASSENEGER_01 | View Past Case Details | Backend | Restrict access to own cases |  | 1 | 1 | To Do | See Backlog row 26
SCRUM-197 | Passenger Operations | PASSENEGER_01 | View Past Case Details | Backend | Load documents and comments |  | 1 | 1 | To Do | See Backlog row 26
SCRUM-198 | Passenger Operations | PASSENEGER_01 | View Past Case Details | Frontend | Make case ID open detailed case view |  | 1 | 1 | To Do | See Backlog row 26
SCRUM-199 | Passenger Operations | PASSENEGER_01 | View Past Case Details | Frontend | Display flight, passenger, documents, and comments |  | 1 | 1 | To Do | See Backlog row 26
SCRUM-200 | Passenger Operations | PASSENEGER_01 | View Past Case Details | Database | Query case details, documents, and comments for passenger case |  | 1 | 1 | To Do | See Backlog row 26
SCRUM-201 | Passenger Operations | PASSENEGER_03 | Attach Documents to Case | Backend | Implement passenger document upload |  | 2 | 2 | To Do | See Backlog row 27
SCRUM-202 | Passenger Operations | PASSENEGER_03 | Attach Documents to Case | Backend | Validate PDF/JPEG/JPG type and 5 MB limit |  | 2 | 2 | To Do | See Backlog row 27
SCRUM-203 | Passenger Operations | PASSENEGER_03 | Attach Documents to Case | Backend | Return upload confirmation |  | 2 | 2 | To Do | See Backlog row 27
SCRUM-204 | Passenger Operations | PASSENEGER_03 | Attach Documents to Case | Frontend | Add drag-and-drop and browse upload field |  | 2 | 2 | To Do | See Backlog row 27
SCRUM-205 | Passenger Operations | PASSENEGER_03 | Attach Documents to Case | Frontend | Show uploaded document in attached documents list |  | 2 | 2 | To Do | See Backlog row 27
SCRUM-206 | Passenger Operations | PASSENEGER_03 | Attach Documents to Case | Frontend | Display toast/snackbar confirmation |  | 2 | 2 | To Do | See Backlog row 27
SCRUM-207 | Passenger Operations | PASSENEGER_03 | Attach Documents to Case | Database | Store uploaded document metadata |  | 2 | 2 | To Do | See Backlog row 27
SCRUM-208 | Passenger Operations | PASSENEGER_03 | Attach Documents to Case | Database | Link document to case and passenger |  | 2 | 2 | To Do | See Backlog row 27
SCRUM-209 | Passenger Operations | PASSENEGER_04 | Download Documents from Case | Backend | Implement passenger document download |  | 2 | 2 | To Do | See Backlog row 28
SCRUM-210 | Passenger Operations | PASSENEGER_04 | Download Documents from Case | Backend | Enforce document access permissions |  | 2 | 2 | To Do | See Backlog row 28
SCRUM-211 | Passenger Operations | PASSENEGER_04 | Download Documents from Case | Frontend | Add document download action |  | 2 | 2 | To Do | See Backlog row 28
SCRUM-212 | Passenger Operations | PASSENEGER_04 | Download Documents from Case | Frontend | Provide user-friendly download behavior |  | 2 | 2 | To Do | See Backlog row 28
SCRUM-213 | Passenger Operations | PASSENEGER_04 | Download Documents from Case | Database | Retrieve document metadata and file reference |  | 2 | 2 | To Do | See Backlog row 28
SCRUM-214 | Passenger Operations | PASSENEGER_05 | Comment on Case | Backend | Add passenger comment API |  | 2 | 2 | To Do | See Backlog row 29
SCRUM-215 | Passenger Operations | PASSENEGER_05 | Comment on Case | Backend | Validate 1000-character limit |  | 2 | 2 | To Do | See Backlog row 29
SCRUM-216 | Passenger Operations | PASSENEGER_05 | Comment on Case | Backend | Timestamp saved comments |  | 2 | 2 | To Do | See Backlog row 29
SCRUM-217 | Passenger Operations | PASSENEGER_05 | Comment on Case | Frontend | Add comment text area and Add Comment button |  | 2 | 2 | To Do | See Backlog row 29
SCRUM-218 | Passenger Operations | PASSENEGER_05 | Comment on Case | Frontend | Show comment list with author and timestamp |  | 2 | 2 | To Do | See Backlog row 29
SCRUM-219 | Passenger Operations | PASSENEGER_05 | Comment on Case | Database | Store passenger comments |  | 2 | 2 | To Do | See Backlog row 29
SCRUM-220 | Passenger Operations | PASSENEGER_05 | Comment on Case | Database | Link comments to case and user |  | 2 | 2 | To Do | See Backlog row 29
SCRUM-221 | System Administration | OPTIONAL_1 | Pre-Loading Airport Data | Backend | Implement scheduled airport data preload job |  | 2 | 3 | To Do | See Backlog row 30
SCRUM-222 | System Administration | OPTIONAL_1 | Pre-Loading Airport Data | Backend | Call external airport REST endpoint |  | 2 | 3 | To Do | See Backlog row 30
SCRUM-223 | System Administration | OPTIONAL_1 | Pre-Loading Airport Data | Backend | Handle refresh errors and retries |  | 2 | 3 | To Do | See Backlog row 30
SCRUM-224 | System Administration | OPTIONAL_1 | Pre-Loading Airport Data | Database | Create or update airports table |  | 2 | 3 | To Do | See Backlog row 30
SCRUM-225 | System Administration | OPTIONAL_1 | Pre-Loading Airport Data | Database | Store airport reference data from API |  | 2 | 3 | To Do | See Backlog row 30

## AI Hackathon Backlog
Epic | Prio | ID | Role | Title | Description | View | Data | Acceptance Criteria | API Call | Task Categorisation
Case Register | 1 | CASE_01 | Passenger | Case Entry | As a passenger, I want to fill out a form that contains personal and flight infos in order to create a new compensation case. | Case Entry Form | Following data must be filled Flight itinerary: - flight date (date), - flight nr.(String), - airline (String), - reservation number (String), - departing airport (API Input), - destination airport (API Input), - connecting flights (API Input), - planned departure time (DateTime), - planned arrival time (DateTime). Passenger details: - firstname (String), - lastname (String), - date of birth (Date<Present Date>), - e-mail (regex), - phone (regex), - address(String), - postal code(String) Documents: - Boarding Pass and ID/Passport (Files: pdf, png, jpg) GDPR details: - 2 fields for "Agree" or "Disagree" with the GDPR policy. | Each case entry form contains 6 distinct parts: 1. flight itinerary 2. disruption details 3. disruption motives 4. email & compliance request 5. flight details 6. passenger details This story does not implement parts 2 and 3, which are implemented in CASE_03 Users can access the case entry form. All required fields are validated before submission. Airport Codes are loaded automatically. The user may add up to 4 connecting flights. The user needs to mark the problem connecting flight (mandatory). Checkbox for GDPR policy. Users must consent in order to be able to submit. Each flight (including connecting flights) will have flight details: flight number, flight date and airline. An upload field is displayed where users must upload a Boarding Pass and ID/Passport. The file size must be a maximum of 5 MB and in PDF or JPEG/JPG format only. All fields are mandatory. A "Status" field is added to the case. It is intially NEW. Four Status are possible: NEW - upon creation, VALID - eligible, ASSIGNED - when a colleague is assigned to a case, INVALID - when a colleague sets it after manual verification. | https://airportgap.com/docs#api_ref_get_airports | Backend: - Case creation API - Airport code lookup integration - Connecting-flight logic - Problem-flight validation - File upload validation - GDPR consent enforcement - Case status workflow Frontend: - Case entry form - Passenger details section - Flight details section - Connecting flights UI - Document upload UI - GDPR checkbox UI - Required-field validation Database: - Case table/model - Passenger data fields - Flight/connection records - Uploaded document metadata - GDPR consent fields - Case status field
Case Register | 1 | CASE_02 | Passenger | Calculate Compensation Level | As a passenger, I want the system to calculate my compensation level based on the flight distance of so that I know how much compensation I am eligible to. | Case Entry Form |  | The system calculates the orthodromic distance between the starting and final destination (connecting flights are not considered). The system determines the compensation level based on the calculated distance: <1500km – 250€ 1500-3500km – 400€ 3500km – 600€ The calculated compensation level is displayed to the user and added as information to the case. | https://airportgap.com/docs#api_ref_post_airports_distance | Backend: - Integrate airport distance API - Calculate orthodromic distance - Apply compensation thresholds - Persist calculated compensation result Frontend: - Display calculated distance - Display compensation amount - Trigger recalculation when airports change Database: - Store distance result - Store compensation amount - Link calculation data to case record
Case Register | 1 | CASE_03 | Passenger | Collect Disruption Motives | As a passenger, I want to provide information about the motive behind the disruption and describe the incident so that my case can be accurately assesed. | Case Entry Form | Disruption Information | The form presents a dropdown menu for the type of disruption (cancellation, delay, denied boarding). Based on the selection, other relevant fields are displayed dynamically. If "Cancellation" is selected: Show fields for "How many days before cancellation has the airline informed?" with options: >14 days, <14 days, on flight day. If "Delay" is selected: Show fields for "How late arrived to final destination?" with options: <3h, >3h, connection flight lost. If "Denied Boarding" is selected: Show field for "Did you give up your seat voluntarily?" with options: Yes, No. If "No" is selected, a follow-up question appears: "Reason behind denial of boarding" with options: Flight overbooked, aggressive behavior with staff, intoxication, unspecified reason. The user should also add additional infos regarding the incident. If "Delay" or "Cancellation" is selected: The form includes a question: "Did the airline mention disruption motive?" with options: Yes, No, I don’t know. If "Yes" is selected, a follow-up question appears: "What was the motive communicated by the airline?" with options: Technical problem, meteorological conditions, strike, problems with airport, crew problems, other motives. If "Delay" or "Cancellation" or "Denied Boarding" is selected: A large text box is provided for users to describe in short what has happened. The text box allows a sufficient character limit to capture detailed descriptions. No Validation Required: The system does not enforce validation on the answers provided for disruption motive questions. A case without infortioan about disruption is not considered valid and may not be submitted. |  | Backend: - Process disruption type selection - Validate disruption presence before submission - Store disruption answers without strict answer validation Frontend: - Build disruption type dropdown - Show conditional fields by disruption type - Add incident description text box - Enforce disruption section completion Database: - Store disruption type - Store cancellation, delay, and denied boarding answers - Store airline motive details - Store incident description
Case Eligibility Verification | 1 | ELIGIBILITY_01 | Passenger | Eligibility Determination | As a passenger, I want the system to determine the eligibility of my case based on my inputs and provide immediate feedback if my case is not eligible so that I know whether to proceed or reconsider my claim. | Backend |  | Eligibility Criteria for Cancellation: The case is eligible if the passenger arrives >3h late or never arrived AND The case is eligible if the cancellation notice was given <14 days or on the flight day. Eligibility Criteria for Delay: The case is eligible if the passenger arrives >3h late or never arrived. Eligibility Criteria for Denied Boarding: The case is eligible if the passenger arrives >3h late or never arrived AND The case is eligible if the passenger did not give up their seat voluntarily. If eligible the "Status" field becomes "VALID". |  | Backend: - Implement eligibility rules for cancellation - Implement eligibility rules for delay - Implement eligibility rules for denied boarding - Set case status to VALID when eligible Frontend: - Show eligibility result feedback - Prevent progression for ineligible cases Database: - Store eligibility outcome - Store eligibility decision inputs - Update case status field
Case Eligibility Verification | 1 | ELIGIBILITY_02 | Passenger | Confirmation of Eligibility | As a passenger, I want to receive a confirmation message when my case is determined to be eligible. | Case Entry Form |  | Only eligible cases can be stored in the database. Eligible Case Confirmation: If the case meets all eligibility criteria, a confirmation (as a simple text: "Case is eligible for submission") is displayed on the page. The "Submit" button becomes clickable. The system sends an email to user that includes a unique case ID for reference. If the case does not meet all eligibility criteria, a confirmation (as a simple text: "Case is NOT eligible for submission") is displayed on the page and the "submit" button remains disabled. |  | Backend: - Enforce only eligible cases can be stored - Generate unique case ID - Trigger confirmation email Frontend: - Show eligible confirmation message - Enable Submit button for eligible cases - Show ineligible confirmation message - Keep Submit button disabled for ineligible cases Database: - Store eligible case record - Persist generated case ID
Case Register | 1 | CASE_04 | (no role) | Save Case | As a passenger, I want the system to create a case based on the entered details. | Backend |  | Case Creation: When the "Submit" button is clicked, the system creates a case with a unique ID and date. A "Colleague" field is automatically added to the case. The field is inially EMPTY until one colleague is assigned. The case includes all entered disruption, flight and passenger details. Disruption Recording: The flight disruption is recorded within the created case. The system ensures all disruption details are accurately captured. All the given details are saved in the database. Database Schema: Ensure the database schema includes tables for cases, flights, passengers, and disruptions. Each table should have appropriate columns to store all relevant details (e.g., case ID, flight date, passenger name). Case Data Storage: When a case is created, all entered details (flight details, passenger details, disruption details) are saved in the respective tables. Ensure that the case ID is unique and acts as a primary key in the cases table. Data Integrity: Validate that all required fields are filled and properly formatted before saving to the database. Implement foreign key constraints to link related data across tables (e.g., linking flights to cases). Error Handling: If saving to the database fails, an appropriate error message is displayed to the user. Ensure that no partial data is saved if the transaction fails. |  | Backend: - Create case with unique ID and date - Add empty colleague assignment field - Save passenger, flight, and disruption details transactionally - Handle database save failures without partial data Frontend: - Submit completed case data - Show save success or error message Database: - Create cases table fields - Create flights table fields - Create passengers table fields - Create disruptions table fields - Add primary and foreign key constraints
Case Register | 1 | CASE_05 | System | Create User Account | As a system, I want to create a user account for a new passenger. | Backend |  | After the system successfully captures and records all relevant information for the new passenger case, including passenger details, flight details, and disruption details, a new user account is created for the passenger. Upon storage of this information in the database, the system automatically generates a new password and sends it to the user's email. The user can then log in using their email address and the newly generated password. This password needs to be changed on the first login. |  | Backend: - Create passenger user account after case data capture - Generate initial password - Send password email - Enforce password change on first login Frontend: - Support login with generated credentials - Prompt password change on first login Database: - Store passenger user account - Store password reset/change-required flag - Link user account to passenger/case data
Case Completion and Documentation | 1 | CASE_COMPLETED_01 | Passenger | Generate PDF with Case Details | As a passenger, I want the system to generate a PDF contract that includes all case and flight details for my reference. | Case Entry Form |  | Entry Form: The form submission button should trigger both the registration and the PDF generation process. PDF Content: The PDF contract includes the case ID, date, passenger details and reservation number. The contract is clearly formatted and contains all necessary information. PDF Generation: If the user submits the form, the system will generate a PDF file containing the details of the newly registered case. The PDF is stored and made available for download. Notification and Access: The confirmation message should include a link to download the generated PDF file. The PDF file should also be accessible from the entry page within the user interface. | https://www.reportlab.com/ | Backend: - Generate PDF contract after form submission - Include case ID, date, passenger details, and reservation number - Store generated PDF - Provide PDF download endpoint Frontend: - Trigger PDF generation on submission - Show PDF download link in confirmation - Make PDF accessible from entry page Database: - Store PDF document metadata - Link PDF file to case record
Case Completion and Documentation | 3 | CASE_COMPLETED_02 | Passenger | Send Email Notification | Send Email to Passenger | Backend |  | Email to Passenger: The system sends an email with the case ID and confirmation that the case was successfully registered. The PDF is attached in case the "Generate PDF". |  | Backend: - Send registration confirmation email - Include case ID in email - Attach generated PDF when available Frontend: - Show email notification confirmation if needed Database: - Store email notification status - Store sent timestamp and delivery metadata
Employee Operations | 1 | EMPLOYEE_03 | Colleague | Case List | As a Colleague, I want to see a list of all the cases in the system. | Case View |  | The system provides access to all cases for colleagues. Past cases are displayed in a list which contains: ID, Case Date, Flight Number, Flight Date, Passenger Name, Status, Colleague assigned to the case (may be empty). |  | Backend: - Provide case list API for colleagues - Apply colleague authorization - Include assigned colleague and status data Frontend: - Build colleague case list view - Display case ID, dates, flight, passenger, status, and assignee - Add navigation to case details Database: - Query cases with passenger, flight, status, and colleague assignment joins
Employee Operations | 1 | EMPLOYEE_01 | Colleague | Create Cases | As a Colleague, I want to create cases so that I can manage work efficiently. | Case Entry Form |  | The system provides options for colleagues to create new cases and flights. The colleague must enter the same information as a regular passenger. See epic 'Case Register'. A confirmation notification (toast/snackbar) is shown upon successful creation. |  | Backend: - Reuse case creation flow for colleagues - Validate passenger, flight, and disruption data - Return creation confirmation Frontend: - Enable colleague case entry form - Show successful creation toast/snackbar Database: - Store colleague-created case records - Link created case to creator if needed
Employee Operations | 1 | EMPLOYEE_05 | Colleague | Case Details | As a Colleague, I want to see the details of a case. | Detailed Case View | Flight, Passenger and Uploaded Documents Details | The system provides access to details of cases for colleagues. The Case ID in the "Case View" is a link. A new page is shown when the link is clicked and should display all the information relevant to a case. The following information is displayed: Flight details: Flight date, Flight Nr., Airline, Reservation Number (XXX), Departing Airport, Destination Airport, Connecting Flights, Planned Departure Time, Planned Arrival Time. Passenger details: Name, Family Name, Date of Birth, Contact details (e-mail, phone, address, postal code). Attached Documents: The documents attached to the case are displayed in an "Attached Documents List". The list contains: Filename, Upload Timestamp. Comments: All comments are shown in a "Comment List" that contains, the user (email address) who commented (Passenger or Colleague) together with a timestamp. |  | Backend: - Provide detailed case API for colleagues - Load flight, passenger, documents, and comments - Enforce colleague access rules Frontend: - Make case ID link open detailed case view - Display full flight, passenger, document, and comment sections Database: - Query related case detail tables - Support document and comment history retrieval
Employee Operations | 2 | EMPLOYEE_02 | Colleague | Comment on Cases | As a Colleague, I want to be able to comment on a case. | Detailed Case View |  | The system allows colleagues in the "Detailed Case View" to add a comment to cases. A large text box is provided for users to comment together with a button labelled "Add Comment". Once the button is pressed the comment is saved and shown in the "Comment List" together with the user who commented (identified by e-mail address). The text box allows a sufficient character limit to capture detailed descriptions. (1000 characters) Comments are time-stamped. |  | Backend: - Add colleague comment API - Validate comment length and author - Timestamp saved comments Frontend: - Add comment text area and button - Show comment list with author and timestamp Database: - Store case comments - Link comments to case and user
Employee Operations | 2 | EMPLOYEE_04 | Colleague | Attach and Download Documents for Cases and Flights | As a Colleague, I want to be able to attach and download documents to/from cases and ensure all necessary information is included. | Detailed Case View |  | The system allows colleagues to upload and download documents related to cases. A confirmation message (toast/snackbar) is shown upon successful document upload/download. The file size must be a maximum of 5 MB and in PDF/JPEG format only. Any newly uploaded document is shown in the "Attached Documents Lists" with the corresponding timestamp. |  | Backend: - Implement colleague document upload and download - Validate file type and 5 MB limit - Return upload/download confirmations Frontend: - Add upload and download controls - Show document list and toast/snackbar confirmation Database: - Store document metadata - Link documents to cases or flights
Employee Operations | 2 | EMPLOYEE_06 | Colleague | Assign Cases to Colleagues | As a Colleague, I want to assign cases to other colleagues to distribute workload efficiently. | Case View |  | The system allows colleagues to assign cases to other colleagues. A dropdown box that contains a list of all colleagues (including the currently logged user because a colleague can assign a case to themselves) is displayed together with a button "Assign" to the "Case View". Once a case and colleague are selected the "Colleague" field for corresponding case is updated. Assigned cases show the correct assignee and status update. Case "Status" field is set to ASSIGNED. Confirmation message (toast/snackbar) is shown to the user. |  | Backend: - Provide colleague list for assignment - Update case assignee - Validate assignment permissions Frontend: - Add colleague dropdown and Assign button - Refresh assignee field after assignment Database: - Store colleague assignment on case - Maintain user-to-case relationship
Employee Operations | 2 | EMPLOYEE_07 | Colleague | Check Eligibility of Flight and Claim | As a Colleague, I want to check the eligibility of a flight and claim so that I can determine if further documentation is needed or if the claim should be rejected. | Case View |  | The system allows colleagues to manually check the case eligibility and set the status of case to "ELIGIBLE" or "NON-ELIGIBLE". A checkbox is added to the 'Case View". Its initial value is taken from the Case. If not eligible, the system automatically sends a rejection response via email (with case ID and new Status) to the passenger and flags the case as INVALID ("Status" field). |  | Backend: - Support manual eligibility status update - Send rejection email for non-eligible cases - Flag rejected case status Frontend: - Add eligibility checkbox/control - Display current case eligibility state - Show update confirmation Database: - Store manual eligibility decision - Update case status and audit fields
Employee Operations | 3 | EMPLOYEE_08 | Colleague | Show PDF History | As a Colleague, I want to see a list of all PDFs generated for the cases in the system, so that I can have a history of all changes. | History View |  | The system provides access to all generated PDFs for the existing cases in the system. Generated PDFs are displayed in a list which contains: ID, Document Name, Passenger Name and Case ID. |  | Backend: - Provide generated PDF history API - Enforce colleague access to PDF history Frontend: - Build PDF history view - Display ID, document name, passenger name, and case ID Database: - Query generated PDF metadata - Link PDFs to cases and passengers
System Administration | 1 | ROLE_00 | System Admin | User List | As a System Admin, I want to see a list of all users in the system. | User View |  | The system provides access to all users in the System. Fields: Name (Firstname + Lastname), E-Mail, Role, number of assigned cases, actions (delete, edit). |  | Backend: - Provide admin user list API - Include assigned case counts - Enforce admin authorization Frontend: - Build user list view - Display name, email, role, assigned cases, and actions Database: - Query users and assigned case counts
System Administration | 1 | ROLE_01 | System Admin | Create User Accounts | As a System Admin, I want to create user accounts for colleagues so that they can access the system and perform their tasks. | New User View | Name, Email | The system allows the creation of new user accounts for colleagues. Confirmation message is shown upon successful account creation. For each new colleague the admin must enter a first name, last name, a valid e-mail address and an intital password. This password is sent to the specified email address and needs to be changed on the first login. |  | Backend: - Implement colleague account creation - Validate new user data - Return creation confirmation Frontend: - Build new user form - Show successful creation confirmation Database: - Store colleague user account - Store assigned role and credentials metadata
System Administration | 2 | ROLE_02 | System Admin | Delete User Accounts | As a System Admin, I want to delete user accounts (passengers, colleagues) to maintain the security and integrity of the system. | User View |  | The system allows the deletion of user accounts for passengers and colleagues. All users are shown in a list that contains the name, e-mail address and a button for deletion (which might already exist from the User List task). Confirmation message is shown upon successful account deletion. |  | Backend: - Implement user deletion endpoint - Validate deletion permissions and constraints - Return deletion confirmation Frontend: - Add delete action to user list - Show deletion confirmation message Database: - Delete or deactivate user accounts - Preserve referential integrity for linked cases
System Administration | 1 | ROLE_03 | System Admin | Delete Cases | As a System Admin, I want to delete cases to manage data effectively. | Case View |  | The system allows the deletion of cases. All cases are displayed in a list which contains ID (link), Case Date, Flight Number, Flight Date, Status, together with a button for deletion. Confirmation message is shown upon successful deletion. |  | Backend: - Implement case deletion endpoint - Validate admin permissions - Return deletion confirmation Frontend: - Add delete button to case list - Show successful deletion confirmation Database: - Delete or archive case records - Handle dependent flight, passenger, document, and comment data
System Administration | 3 | ROLE_04 | System Admin | Admin Landing Page | As a System Admin I want to see a landing page that contains all the possible actions I can perform. | Admin View |  | The System shows a landing page that guides the Admin with links to the other relevant pages: New User View, User View, Case View, System View. |  | Backend: - Provide admin navigation metadata if needed - Enforce admin-only access Frontend: - Build admin landing page - Add links to New User, User, Case, and System views Database: - No new persistent data required
System Administration | 3 | ROLE_05 | System Admin | Change System Options | As a System Admin, I want to change system options (e-mail accounts, SMTP servers, e-mail presets, PDF presets) to ensure the system is configured correctly and meets the needs of the organisation. | System View |  | The story is optional; the settings details are left to the implementors preference. The system allows changing system options such as email presets, and pdf presets. Email presets can include which e-mail system/api is used, formatting options, placeholder texts, etc. PDF presets can include which fields are exported, layout, etc. Changes are correctly applied and reflected in the system settings. |  | Backend: - Implement system options management - Support email preset and PDF preset configuration - Validate configuration changes Frontend: - Build system options view - Add editable email and PDF preset fields - Show save confirmation Database: - Store system option records - Persist email and PDF preset settings
Passenger Operations | 1 | PASSENEGER_02 | Passenger | View Past Cases | As a registered Passenger, I want to see my past cases so that I can review their status and details. | Case View |  | The system provides access to past cases for registered passengers. Past cases are displayed in a list which contains: ID, Flight Number, Passenger Name, Status, Colleague assigned to the case (may be empty). |  | Backend: - Provide passenger case list API - Restrict results to logged-in passenger Frontend: - Build passenger past cases view - Display ID, flight number, passenger name, status, and assignee Database: - Query cases linked to passenger account
Passenger Operations | 1 | PASSENEGER_01 | Passenger | View Past Case Details | As a registered Passenger, I want to see the datails of a past case. | Detailed Case View | Flight, Passenger and Uploaded Documents Details | The system provides access to details of past cases for registered passengers. The Case ID in the "Case View" is a link. A new page is shown when the link is clicked and should display all the information relevant to a case. The following information is displayed: Flight details: Flight date, Flight Nr., Airline, Reservation Number (XXX), Departing Airport, Destination Airport, Connecting Flights, Planned Departure Time, Planned Arrival Time. Passenger details: Name, Family Name, Date of Birth, Contact details (e-mail, phone, address, postal code). Attached Documents: The any documents are attached to the case they are displayed in a "Attached Documents Lists". The list contains: Filename, Upload Timestamp. Comments: All comments are shown in a "Comment List" that contains, the user (email address) who commented (Passenger or Colleague) together with a timestamp. |  | Backend: - Provide passenger case details API - Restrict access to own cases - Load documents and comments Frontend: - Make case ID open detailed case view - Display flight, passenger, documents, and comments Database: - Query case details, documents, and comments for passenger case
Passenger Operations | 2 | PASSENEGER_03 | Passenger | Attach Documents to Case | As a Passenger, I want to attach documents to my cases so that I can provide necessary information. | Detailed Case View |  | The system allows registered passengers in the "Detailed Case View" to upload documents to their cases. An upload field is added to the view, with the option to either drag and drop, or browse in the file system. The file size must be a maximum of 5 MB and in PDF/JPEG/JPG format only. A confirmation message (toast/snackbar) is shown upon successful upload of documents. Any newly uploaded document is shown in the "Attached Documents Lists" with the corresponding timestamp. |  | Backend: - Implement passenger document upload - Validate PDF/JPEG/JPG type and 5 MB limit - Return upload confirmation Frontend: - Add drag-and-drop and browse upload field - Show uploaded document in attached documents list - Display toast/snackbar confirmation Database: - Store uploaded document metadata - Link document to case and passenger
Passenger Operations | 2 | PASSENEGER_04 | Passenger | Download Documents from Case | As a Passenger, I want to download documents from my cases so that I can keep a record of them. | Detailed Case View |  | The system allows passengers in the "Detailed Case View" to download documents from their cases. Documents are downloaded in a user-friendly format. |  | Backend: - Implement passenger document download - Enforce document access permissions Frontend: - Add document download action - Provide user-friendly download behavior Database: - Retrieve document metadata and file reference
Passenger Operations | 2 | PASSENEGER_05 | Passenger | Comment on Case | As a Passenger, I want to comment on my cases as a means of communication to provide additional information or ask questions. | Detailed Case View |  | The system allows passengers in the "Detailed Case View" to add a comment to their cases. A large text box is provided for users to comment, together with a button labelled "Add Comment". Once the button is pressed the comment is saved and shown in the "Comment List" together with the user who commented (identified by e-mail address). The text box allows a sufficient character limit to capture detailed descriptions (1000 characters). Comments are time-stamped. |  | Backend: - Add passenger comment API - Validate 1000-character limit - Timestamp saved comments Frontend: - Add comment text area and Add Comment button - Show comment list with author and timestamp Database: - Store passenger comments - Link comments to case and user
System Administration | 3 | OPTIONAL_1 | System (no role) | Pre-Loading Airport Data | To reduce the number of REST Calls, a Timed-Job must be implemented that fills the Airports DB Table with Data from the REST API |  |  | The system runs a timed-kob that refills the Airports table with Data from an external REST endpoint. |  | Backend: - Implement scheduled airport data preload job - Call external airport REST endpoint - Handle refresh errors and retries Frontend: - No direct UI required unless monitoring is added Database: - Create or update airports table - Store airport reference data from API
Note on I2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Propunere API in dreapta
Note on I3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Propunere API in dreapta
Note on I20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Technical Details for the Self-Study part: 1. [2-1-django-project-structure-and-configuration.md] - Create a new Django project called AirAssistBackend 2. [2-3-django-models-and-database-integration.md] - Create a Database in PostgresSQL called AirAssist - Create Table Users[userId, roleId, firstName, lastName, email, password] - Create Table Roles[roleId, role]. Role is a string withe the following options: System_Admin, Colleague, Passenger -Configure Project to use PostgresSQL - Create a model for User - Create a model for Role 3. [2-4-django-orm.md] - Add a method to create a user - Add a method to get the role of a specific user 4. [2-5-django-rest-framework.md] - Create a POST endpoint that creates a new user: POST /user valid body → 201 {userId, roleId, firstName, lastName, email} - Create a GET endpoint that returns the role for a specific user: GET /user/1 valid body → 200 {roleId, role} 5. [2-7-django-authentication-and-authorization] - setup JWT authentication for the project - Create A login page with two inputs (email, password) that allows a user to login. The page will display a text 'Success' if the loggin is successful, or fobidden otherwise. - Create a permission is_system_admin that allows admin users to create a new users and include this permission for the endpoint: POST /user - A regular user can only use the the endpoint: GET /user/<id> 6. [3-0-special-topics.md] - Change. the creation endpoint so that the users receives upon creation an email with is details: userId, roleId, firstName, lastName, email and password Reply: This Story will be implemented in Phase 1 - Focus Self-Learning (minus the change password functionality - that will come later) The objective of the story is to have a functioning project skeleton when you start work on the project (Phase 2)
Note on I21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Trebuie intrebat ce se intampla cu "case"urile asignate unui user

## Backlog (hidden)
Epic | Prio | ID | Role | Title | Description | View | Data | Acceptance Criteria | API Call | Task Categorisation
Case Register | 1 | CASE_01 | Passenger | Case Entry | As a passenger, I want to fill out a form that contains personal and flight infos in order to create a new compensation case. | Case Entry Form | Following data must be filled Flight itinerary: - flight date (date), - flight nr.(String), - airline (String), - reservation number (String), - departing airport (API Input), - destination airport (API Input), - connecting flights (API Input), - planned departure time (DateTime), - planned arrival time (DateTime). Passenger details: - firstname (String), - lastname (String), - date of birth (Date<Present Date>), - e-mail (regex), - phone (regex), - address(String), - postal code(String) Documents: - Boarding Pass and ID/Passport (Files: pdf, png, jpg) GDPR details: - 2 fields for "Agree" or "Disagree" with the GDPR policy. | Each case entry form contains 6 distinct parts: 1. flight itinerary 2. disruption details 3. disruption motives 4. email & compliance request 5. flight details 6. passenger details This story does not implement parts 2 and 3, which are implemented in CASE_03 Users can access the case entry form. All required fields are validated before submission. Airport Codes are loaded automatically. The user may add up to 4 connecting flights. The user needs to mark the problem connecting flight (mandatory). Checkbox for GDPR policy. Users must consent in order to be able to submit. Each flight (including connecting flights) will have flight details: flight number, flight date and airline. An upload field is displayed where users must upload a Boarding Pass and ID/Passport. The file size must be a maximum of 5 MB and in PDF or JPEG/JPG format only. All fields are mandatory. A "Status" field is added to the case. It is intially NEW. Four Status are possible: NEW - upon creation, VALID - eligible, ASSIGNED - when a colleague is assigned to a case, INVALID - when a colleague sets it after manual verification. | https://airportgap.com/docs#api_ref_get_airports | Backend: - Case creation API - Airport code lookup integration - Connecting-flight logic - Problem-flight validation - File upload validation - GDPR consent enforcement - Case status workflow Frontend: - Case entry form - Passenger details section - Flight details section - Connecting flights UI - Document upload UI - GDPR checkbox UI - Required-field validation Database: - Case table/model - Passenger data fields - Flight/connection records - Uploaded document metadata - GDPR consent fields - Case status field
Case Register | 1 | CASE_02 | Passenger | Calculate Compensation Level | As a passenger, I want the system to calculate my compensation level based on the flight distance of so that I know how much compensation I am eligible to. | Case Entry Form |  | The system calculates the orthodromic distance between the starting and final destination (connecting flights are not considered). The system determines the compensation level based on the calculated distance: <1500km – 250€ 1500-3500km – 400€ 3500km – 600€ The calculated compensation level is displayed to the user and added as information to the case. | https://airportgap.com/docs#api_ref_post_airports_distance | Backend: - Integrate airport distance API - Calculate orthodromic distance - Apply compensation thresholds - Persist calculated compensation result Frontend: - Display calculated distance - Display compensation amount - Trigger recalculation when airports change Database: - Store distance result - Store compensation amount - Link calculation data to case record
Case Register | 1 | CASE_03 | Passenger | Collect Disruption Motives | As a passenger, I want to provide information about the motive behind the disruption and describe the incident so that my case can be accurately assesed. | Case Entry Form | Disruption Information | The form presents a dropdown menu for the type of disruption (cancellation, delay, denied boarding). Based on the selection, other relevant fields are displayed dynamically. If "Cancellation" is selected: Show fields for "How many days before cancellation has the airline informed?" with options: >14 days, <14 days, on flight day. If "Delay" is selected: Show fields for "How late arrived to final destination?" with options: <3h, >3h, connection flight lost. If "Denied Boarding" is selected: Show field for "Did you give up your seat voluntarily?" with options: Yes, No. If "No" is selected, a follow-up question appears: "Reason behind denial of boarding" with options: Flight overbooked, aggressive behavior with staff, intoxication, unspecified reason. The user should also add additional infos regarding the incident. If "Delay" or "Cancellation" is selected: The form includes a question: "Did the airline mention disruption motive?" with options: Yes, No, I don’t know. If "Yes" is selected, a follow-up question appears: "What was the motive communicated by the airline?" with options: Technical problem, meteorological conditions, strike, problems with airport, crew problems, other motives. If "Delay" or "Cancellation" or "Denied Boarding" is selected: A large text box is provided for users to describe in short what has happened. The text box allows a sufficient character limit to capture detailed descriptions. No Validation Required: The system does not enforce validation on the answers provided for disruption motive questions. A case without infortioan about disruption is not considered valid and may not be submitted. |  | Backend: - Process disruption type selection - Validate disruption presence before submission - Store disruption answers without strict answer validation Frontend: - Build disruption type dropdown - Show conditional fields by disruption type - Add incident description text box - Enforce disruption section completion Database: - Store disruption type - Store cancellation, delay, and denied boarding answers - Store airline motive details - Store incident description
Case Eligibility Verification | 1 | ELIGIBILITY_01 | Passenger | Eligibility Determination | As a passenger, I want the system to determine the eligibility of my case based on my inputs and provide immediate feedback if my case is not eligible so that I know whether to proceed or reconsider my claim. | Backend |  | Eligibility Criteria for Cancellation: The case is eligible if the passenger arrives >3h late or never arrived AND The case is eligible if the cancellation notice was given <14 days or on the flight day. Eligibility Criteria for Delay: The case is eligible if the passenger arrives >3h late or never arrived. Eligibility Criteria for Denied Boarding: The case is eligible if the passenger arrives >3h late or never arrived AND The case is eligible if the passenger did not give up their seat voluntarily. If eligible the "Status" field becomes "VALID". |  | Backend: - Implement eligibility rules for cancellation - Implement eligibility rules for delay - Implement eligibility rules for denied boarding - Set case status to VALID when eligible Frontend: - Show eligibility result feedback - Prevent progression for ineligible cases Database: - Store eligibility outcome - Store eligibility decision inputs - Update case status field
Case Eligibility Verification | 1 | ELIGIBILITY_02 | Passenger | Confirmation of Eligibility | As a passenger, I want to receive a confirmation message when my case is determined to be eligible. | Case Entry Form |  | Only eligible cases can be stored in the database. Eligible Case Confirmation: If the case meets all eligibility criteria, a confirmation (as a simple text: "Case is eligible for submission") is displayed on the page. The "Submit" button becomes clickable. The system sends an email to user that includes a unique case ID for reference. If the case does not meet all eligibility criteria, a confirmation (as a simple text: "Case is NOT eligible for submission") is displayed on the page and the "submit" button remains disabled. |  | Backend: - Enforce only eligible cases can be stored - Generate unique case ID - Trigger confirmation email Frontend: - Show eligible confirmation message - Enable Submit button for eligible cases - Show ineligible confirmation message - Keep Submit button disabled for ineligible cases Database: - Store eligible case record - Persist generated case ID
Case Register | 1 | CASE_04 | (no role) | Save Case | As a passenger, I want the system to create a case based on the entered details. | Backend |  | Case Creation: When the "Submit" button is clicked, the system creates a case with a unique ID and date. A "Colleague" field is automatically added to the case. The field is inially EMPTY until one colleague is assigned. The case includes all entered disruption, flight and passenger details. Disruption Recording: The flight disruption is recorded within the created case. The system ensures all disruption details are accurately captured. All the given details are saved in the database. Database Schema: Ensure the database schema includes tables for cases, flights, passengers, and disruptions. Each table should have appropriate columns to store all relevant details (e.g., case ID, flight date, passenger name). Case Data Storage: When a case is created, all entered details (flight details, passenger details, disruption details) are saved in the respective tables. Ensure that the case ID is unique and acts as a primary key in the cases table. Data Integrity: Validate that all required fields are filled and properly formatted before saving to the database. Implement foreign key constraints to link related data across tables (e.g., linking flights to cases). Error Handling: If saving to the database fails, an appropriate error message is displayed to the user. Ensure that no partial data is saved if the transaction fails. |  | Backend: - Create case with unique ID and date - Add empty colleague assignment field - Save passenger, flight, and disruption details transactionally - Handle database save failures without partial data Frontend: - Submit completed case data - Show save success or error message Database: - Create cases table fields - Create flights table fields - Create passengers table fields - Create disruptions table fields - Add primary and foreign key constraints
Case Register | 1 | CASE_05 | System | Create User Account | As a system, I want to create a user account for a new passenger. | Backend |  | After the system successfully captures and records all relevant information for the new passenger case, including passenger details, flight details, and disruption details, a new user account is created for the passenger. Upon storage of this information in the database, the system automatically generates a new password and sends it to the user's email. The user can then log in using their email address and the newly generated password. This password needs to be changed on the first login. |  | Backend: - Create passenger user account after case data capture - Generate initial password - Send password email - Enforce password change on first login Frontend: - Support login with generated credentials - Prompt password change on first login Database: - Store passenger user account - Store password reset/change-required flag - Link user account to passenger/case data
Case Completion and Documentation | 1 | CASE_COMPLETED_01 | Passenger | Generate PDF with Case Details | As a passenger, I want the system to generate a PDF contract that includes all case and flight details for my reference. | Case Entry Form |  | Entry Form: The form submission button should trigger both the registration and the PDF generation process. PDF Content: The PDF contract includes the case ID, date, passenger details and reservation number. The contract is clearly formatted and contains all necessary information. PDF Generation: If the user submits the form, the system will generate a PDF file containing the details of the newly registered case. The PDF is stored and made available for download. Notification and Access: The confirmation message should include a link to download the generated PDF file. The PDF file should also be accessible from the entry page within the user interface. | https://www.reportlab.com/ | Backend: - Generate PDF contract after form submission - Include case ID, date, passenger details, and reservation number - Store generated PDF - Provide PDF download endpoint Frontend: - Trigger PDF generation on submission - Show PDF download link in confirmation - Make PDF accessible from entry page Database: - Store PDF document metadata - Link PDF file to case record
Case Completion and Documentation | 3 | CASE_COMPLETED_02 | Passenger | Send Email Notification | Send Email to Passenger | Backend |  | Email to Passenger: The system sends an email with the case ID and confirmation that the case was successfully registered. The PDF is attached in case the "Generate PDF". |  | Backend: - Send registration confirmation email - Include case ID in email - Attach generated PDF when available Frontend: - Show email notification confirmation if needed Database: - Store email notification status - Store sent timestamp and delivery metadata
Employee Operations | 1 | EMPLOYEE_03 | Colleague | Case List | As a Colleague, I want to see a list of all the cases in the system. | Case View |  | The system provides access to all cases for colleagues. Past cases are displayed in a list which contains: ID, Case Date, Flight Number, Flight Date, Passenger Name, Status, Colleague assigned to the case (may be empty). |  | Backend: - Provide case list API for colleagues - Apply colleague authorization - Include assigned colleague and status data Frontend: - Build colleague case list view - Display case ID, dates, flight, passenger, status, and assignee - Add navigation to case details Database: - Query cases with passenger, flight, status, and colleague assignment joins
Employee Operations | 1 | EMPLOYEE_01 | Colleague | Create Cases | As a Colleague, I want to create cases so that I can manage work efficiently. | Case Entry Form |  | The system provides options for colleagues to create new cases and flights. The colleague must enter the same information as a regular passenger. See epic 'Case Register'. A confirmation notification (toast/snackbar) is shown upon successful creation. |  | Backend: - Reuse case creation flow for colleagues - Validate passenger, flight, and disruption data - Return creation confirmation Frontend: - Enable colleague case entry form - Show successful creation toast/snackbar Database: - Store colleague-created case records - Link created case to creator if needed
Employee Operations | 1 | EMPLOYEE_05 | Colleague | Case Details | As a Colleague, I want to see the details of a case. | Detailed Case View | Flight, Passenger and Uploaded Documents Details | The system provides access to details of cases for colleagues. The Case ID in the "Case View" is a link. A new page is shown when the link is clicked and should display all the information relevant to a case. The following information is displayed: Flight details: Flight date, Flight Nr., Airline, Reservation Number (XXX), Departing Airport, Destination Airport, Connecting Flights, Planned Departure Time, Planned Arrival Time. Passenger details: Name, Family Name, Date of Birth, Contact details (e-mail, phone, address, postal code). Attached Documents: The documents attached to the case are displayed in an "Attached Documents List". The list contains: Filename, Upload Timestamp. Comments: All comments are shown in a "Comment List" that contains, the user (email address) who commented (Passenger or Colleague) together with a timestamp. |  | Backend: - Provide detailed case API for colleagues - Load flight, passenger, documents, and comments - Enforce colleague access rules Frontend: - Make case ID link open detailed case view - Display full flight, passenger, document, and comment sections Database: - Query related case detail tables - Support document and comment history retrieval
Employee Operations | 2 | EMPLOYEE_02 | Colleague | Comment on Cases | As a Colleague, I want to be able to comment on a case. | Detailed Case View |  | The system allows colleagues in the "Detailed Case View" to add a comment to cases. A large text box is provided for users to comment together with a button labelled "Add Comment". Once the button is pressed the comment is saved and shown in the "Comment List" together with the user who commented (identified by e-mail address). The text box allows a sufficient character limit to capture detailed descriptions. (1000 characters) Comments are time-stamped. |  | Backend: - Add colleague comment API - Validate comment length and author - Timestamp saved comments Frontend: - Add comment text area and button - Show comment list with author and timestamp Database: - Store case comments - Link comments to case and user
Employee Operations | 2 | EMPLOYEE_04 | Colleague | Attach and Download Documents for Cases and Flights | As a Colleague, I want to be able to attach and download documents to/from cases and ensure all necessary information is included. | Detailed Case View |  | The system allows colleagues to upload and download documents related to cases. A confirmation message (toast/snackbar) is shown upon successful document upload/download. The file size must be a maximum of 5 MB and in PDF/JPEG format only. Any newly uploaded document is shown in the "Attached Documents Lists" with the corresponding timestamp. |  | Backend: - Implement colleague document upload and download - Validate file type and 5 MB limit - Return upload/download confirmations Frontend: - Add upload and download controls - Show document list and toast/snackbar confirmation Database: - Store document metadata - Link documents to cases or flights
Employee Operations | 2 | EMPLOYEE_06 | Colleague | Assign Cases to Colleagues | As a Colleague, I want to assign cases to other colleagues to distribute workload efficiently. | Case View |  | The system allows colleagues to assign cases to other colleagues. A dropdown box that contains a list of all colleagues (including the currently logged user because a colleague can assign a case to themselves) is displayed together with a button "Assign" to the "Case View". Once a case and colleague are selected the "Colleague" field for corresponding case is updated. Assigned cases show the correct assignee and status update. Case "Status" field is set to ASSIGNED. Confirmation message (toast/snackbar) is shown to the user. |  | Backend: - Provide colleague list for assignment - Update case assignee - Validate assignment permissions Frontend: - Add colleague dropdown and Assign button - Refresh assignee field after assignment Database: - Store colleague assignment on case - Maintain user-to-case relationship
Employee Operations | 2 | EMPLOYEE_07 | Colleague | Check Eligibility of Flight and Claim | As a Colleague, I want to check the eligibility of a flight and claim so that I can determine if further documentation is needed or if the claim should be rejected. | Case View |  | The system allows colleagues to manually check the case eligibility and set the status of case to "ELIGIBLE" or "NON-ELIGIBLE". A checkbox is added to the 'Case View". Its initial value is taken from the Case. If not eligible, the system automatically sends a rejection response via email (with case ID and new Status) to the passenger and flags the case as INVALID ("Status" field). |  | Backend: - Support manual eligibility status update - Send rejection email for non-eligible cases - Flag rejected case status Frontend: - Add eligibility checkbox/control - Display current case eligibility state - Show update confirmation Database: - Store manual eligibility decision - Update case status and audit fields
Employee Operations | 3 | EMPLOYEE_08 | Colleague | Show PDF History | As a Colleague, I want to see a list of all PDFs generated for the cases in the system, so that I can have a history of all changes. | History View |  | The system provides access to all generated PDFs for the existing cases in the system. Generated PDFs are displayed in a list which contains: ID, Document Name, Passenger Name and Case ID. |  | Backend: - Provide generated PDF history API - Enforce colleague access to PDF history Frontend: - Build PDF history view - Display ID, document name, passenger name, and case ID Database: - Query generated PDF metadata - Link PDFs to cases and passengers
System Administration | 1 | ROLE_00 | System Admin | User List | As a System Admin, I want to see a list of all users in the system. | User View |  | The system provides access to all users in the System. Fields: Name (Firstname + Lastname), E-Mail, Role, number of assigned cases, actions (delete, edit). |  | Backend: - Provide admin user list API - Include assigned case counts - Enforce admin authorization Frontend: - Build user list view - Display name, email, role, assigned cases, and actions Database: - Query users and assigned case counts
System Administration | 1 | ROLE_01 | System Admin | Create User Accounts | As a System Admin, I want to create user accounts for colleagues so that they can access the system and perform their tasks. | New User View | Name, Email | The system allows the creation of new user accounts for colleagues. Confirmation message is shown upon successful account creation. For each new colleague the admin must enter a first name, last name, a valid e-mail address and an intital password. This password is sent to the specified email address and needs to be changed on the first login. |  | Backend: - Implement colleague account creation - Validate new user data - Return creation confirmation Frontend: - Build new user form - Show successful creation confirmation Database: - Store colleague user account - Store assigned role and credentials metadata
System Administration | 2 | ROLE_02 | System Admin | Delete User Accounts | As a System Admin, I want to delete user accounts (passengers, colleagues) to maintain the security and integrity of the system. | User View |  | The system allows the deletion of user accounts for passengers and colleagues. All users are shown in a list that contains the name, e-mail address and a button for deletion (which might already exist from the User List task). Confirmation message is shown upon successful account deletion. |  | Backend: - Implement user deletion endpoint - Validate deletion permissions and constraints - Return deletion confirmation Frontend: - Add delete action to user list - Show deletion confirmation message Database: - Delete or deactivate user accounts - Preserve referential integrity for linked cases
System Administration | 1 | ROLE_03 | System Admin | Delete Cases | As a System Admin, I want to delete cases to manage data effectively. | Case View |  | The system allows the deletion of cases. All cases are displayed in a list which contains ID (link), Case Date, Flight Number, Flight Date, Status, together with a button for deletion. Confirmation message is shown upon successful deletion. |  | Backend: - Implement case deletion endpoint - Validate admin permissions - Return deletion confirmation Frontend: - Add delete button to case list - Show successful deletion confirmation Database: - Delete or archive case records - Handle dependent flight, passenger, document, and comment data
System Administration | 3 | ROLE_04 | System Admin | Admin Landing Page | As a System Admin I want to see a landing page that contains all the possible actions I can perform. | Admin View |  | The System shows a landing page that guides the Admin with links to the other relevant pages: New User View, User View, Case View, System View. |  | Backend: - Provide admin navigation metadata if needed - Enforce admin-only access Frontend: - Build admin landing page - Add links to New User, User, Case, and System views Database: - No new persistent data required
System Administration | 3 | ROLE_05 | System Admin | Change System Options | As a System Admin, I want to change system options (e-mail accounts, SMTP servers, e-mail presets, PDF presets) to ensure the system is configured correctly and meets the needs of the organisation. | System View |  | The story is optional; the settings details are left to the implementors preference. The system allows changing system options such as email presets, and pdf presets. Email presets can include which e-mail system/api is used, formatting options, placeholder texts, etc. PDF presets can include which fields are exported, layout, etc. Changes are correctly applied and reflected in the system settings. |  | Backend: - Implement system options management - Support email preset and PDF preset configuration - Validate configuration changes Frontend: - Build system options view - Add editable email and PDF preset fields - Show save confirmation Database: - Store system option records - Persist email and PDF preset settings
Passenger Operations | 1 | PASSENEGER_02 | Passenger | View Past Cases | As a registered Passenger, I want to see my past cases so that I can review their status and details. | Case View |  | The system provides access to past cases for registered passengers. Past cases are displayed in a list which contains: ID, Flight Number, Passenger Name, Status, Colleague assigned to the case (may be empty). |  | Backend: - Provide passenger case list API - Restrict results to logged-in passenger Frontend: - Build passenger past cases view - Display ID, flight number, passenger name, status, and assignee Database: - Query cases linked to passenger account
Passenger Operations | 1 | PASSENEGER_01 | Passenger | View Past Case Details | As a registered Passenger, I want to see the datails of a past case. | Detailed Case View | Flight, Passenger and Uploaded Documents Details | The system provides access to details of past cases for registered passengers. The Case ID in the "Case View" is a link. A new page is shown when the link is clicked and should display all the information relevant to a case. The following information is displayed: Flight details: Flight date, Flight Nr., Airline, Reservation Number (XXX), Departing Airport, Destination Airport, Connecting Flights, Planned Departure Time, Planned Arrival Time. Passenger details: Name, Family Name, Date of Birth, Contact details (e-mail, phone, address, postal code). Attached Documents: The any documents are attached to the case they are displayed in a "Attached Documents Lists". The list contains: Filename, Upload Timestamp. Comments: All comments are shown in a "Comment List" that contains, the user (email address) who commented (Passenger or Colleague) together with a timestamp. |  | Backend: - Provide passenger case details API - Restrict access to own cases - Load documents and comments Frontend: - Make case ID open detailed case view - Display flight, passenger, documents, and comments Database: - Query case details, documents, and comments for passenger case
Passenger Operations | 2 | PASSENEGER_03 | Passenger | Attach Documents to Case | As a Passenger, I want to attach documents to my cases so that I can provide necessary information. | Detailed Case View |  | The system allows registered passengers in the "Detailed Case View" to upload documents to their cases. An upload field is added to the view, with the option to either drag and drop, or browse in the file system. The file size must be a maximum of 5 MB and in PDF/JPEG/JPG format only. A confirmation message (toast/snackbar) is shown upon successful upload of documents. Any newly uploaded document is shown in the "Attached Documents Lists" with the corresponding timestamp. |  | Backend: - Implement passenger document upload - Validate PDF/JPEG/JPG type and 5 MB limit - Return upload confirmation Frontend: - Add drag-and-drop and browse upload field - Show uploaded document in attached documents list - Display toast/snackbar confirmation Database: - Store uploaded document metadata - Link document to case and passenger
Passenger Operations | 2 | PASSENEGER_04 | Passenger | Download Documents from Case | As a Passenger, I want to download documents from my cases so that I can keep a record of them. | Detailed Case View |  | The system allows passengers in the "Detailed Case View" to download documents from their cases. Documents are downloaded in a user-friendly format. |  | Backend: - Implement passenger document download - Enforce document access permissions Frontend: - Add document download action - Provide user-friendly download behavior Database: - Retrieve document metadata and file reference
Passenger Operations | 2 | PASSENEGER_05 | Passenger | Comment on Case | As a Passenger, I want to comment on my cases as a means of communication to provide additional information or ask questions. | Detailed Case View |  | The system allows passengers in the "Detailed Case View" to add a comment to their cases. A large text box is provided for users to comment, together with a button labelled "Add Comment". Once the button is pressed the comment is saved and shown in the "Comment List" together with the user who commented (identified by e-mail address). The text box allows a sufficient character limit to capture detailed descriptions (1000 characters). Comments are time-stamped. |  | Backend: - Add passenger comment API - Validate 1000-character limit - Timestamp saved comments Frontend: - Add comment text area and Add Comment button - Show comment list with author and timestamp Database: - Store passenger comments - Link comments to case and user
System Administration | 3 | OPTIONAL_1 | System (no role) | Pre-Loading Airport Data | To reduce the number of REST Calls, a Timed-Job must be implemented that fills the Airports DB Table with Data from the REST API |  |  | The system runs a timed-kob that refills the Airports table with Data from an external REST endpoint. |  | Backend: - Implement scheduled airport data preload job - Call external airport REST endpoint - Handle refresh errors and retries Frontend: - No direct UI required unless monitoring is added Database: - Create or update airports table - Store airport reference data from API
Note on I2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Propunere API in dreapta
Note on I3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Propunere API in dreapta
Note on I20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Technical Details for the Self-Study part: 1. [2-1-django-project-structure-and-configuration.md] - Create a new Django project called AirAssistBackend 2. [2-3-django-models-and-database-integration.md] - Create a Database in PostgresSQL called AirAssist - Create Table Users[userId, roleId, firstName, lastName, email, password] - Create Table Roles[roleId, role]. Role is a string withe the following options: System_Admin, Colleague, Passenger -Configure Project to use PostgresSQL - Create a model for User - Create a model for Role 3. [2-4-django-orm.md] - Add a method to create a user - Add a method to get the role of a specific user 4. [2-5-django-rest-framework.md] - Create a POST endpoint that creates a new user: POST /user valid body → 201 {userId, roleId, firstName, lastName, email} - Create a GET endpoint that returns the role for a specific user: GET /user/1 valid body → 200 {roleId, role} 5. [2-7-django-authentication-and-authorization] - setup JWT authentication for the project - Create A login page with two inputs (email, password) that allows a user to login. The page will display a text 'Success' if the loggin is successful, or fobidden otherwise. - Create a permission is_system_admin that allows admin users to create a new users and include this permission for the endpoint: POST /user - A regular user can only use the the endpoint: GET /user/<id> 6. [3-0-special-topics.md] - Change. the creation endpoint so that the users receives upon creation an email with is details: userId, roleId, firstName, lastName, email and password Reply: This Story will be implemented in Phase 1 - Focus Self-Learning (minus the change password functionality - that will come later) The objective of the story is to have a functioning project skeleton when you start work on the project (Phase 2)
Note on I21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Trebuie intrebat ce se intampla cu "case"urile asignate unui user

## Scrum Settings (hidden)
Students | How to update
Catalina | Edit Student 1–5 names in column A. If you add more students, extend the dropdown source range on the Scrum Board Student column.
Calin
Darius
Filip
Gabriel

## User types & actions
User Type | User Story
Passenger | As a Passenger (registered), I want to create cases so that I can report issues or requests.
As a Passenger (non-registered), I want to create cases so that I can report issues without having to register.
As a registered Passenger, I want to see my past cases so that I can review their status and details.
As a Passenger, I want to attach documents to my cases so that I can provide necessary information.
As a Passenger, I want to download documents from my cases so that I can keep a record of them.
As a Passenger, I want to comment on my cases as a means of communication to provide additional information or ask questions.
Attorney | Attorneys are not allowed in the system.
Colleague | As a Colleague, I want to create cases, claim cases, and flights so that I can manage work effectively.
As a Colleague, I want to comment on cases and claim cases as a means of communication to collaborate with others.
As a Colleague, I want to create user accounts for passengers to help them access the system.
As a Colleague, I want to attach documents to/from cases, claim cases, and flights to ensure all necessary information is included.
As a Colleague, I want to link cases to claim cases to maintain proper case management.
As a Colleague, I want to link flights to cases so that I can track relevant flight details.
As a Colleague, I want to assign cases to other colleagues to distribute workload efficiently.
As a Colleague, I want to assign claim cases to attorneys (if they were allowed) to ensure proper legal handling.
As a Colleague, I want to check the eligibility of a flight and claim so that I can determine if further documentation is needed or if the claim should be rejected.
System Admin | As a System Admin, I want to create users (passengers, colleagues, attorneys) so that they can access the system and perform their tasks. - Admin View
As a System Admin, I want to delete users (passengers, colleagues, attorneys) to maintain the security and integrity of the system.
As a System Admin, I want to delete cases, claim cases, and flights to manage data effectively.
As a System Admin, I want to modify/reset user accounts to assist users who are facing issues with their accounts.
As a System Admin, I want to change system options (email accounts/SMTP servers, email presets, pdf presets) to ensure the system is configured correctly and meets the needs of the organization.

## Case entry flow 12.08.24 (hidden)
UPDATE 12.08.2024 A case entry form is one of the most important piece of the application and has a few steps. We had every story for it written, however how these stories interconnect/the flow of them was missing. Now you can find below the flow of case entry and how each story connects: ACCESS OF FORM - the case entry form can be accessed as registerered user from the case overview page or as a non-registered user from the home page - on the home page there are two buttons: "verify your flights eligibility" - this opens a new form and the button "view existing case" wich goes to the login page FLOW OF THE FORM AND CASE REGISTRY The form has the following flow: 1. FLIGHT DETAILS - here we want to calculate the distance and determine the compensation value - see CASE_01 and CASE_02 - The distance is calculated based on the distance between the starting point and destination - We want also here to capture any other flights in the same reservation: after the passenger entered the starting point and destination, he can add also stopovers. Stopovers are also airports. From this we can determine, how many flight there were in the yourney: passenger enters the journey CLJ-LHR - from this we will know the distance. He/she also adds a stopover in MUC. From this we have the flight legs: CLJ-MUC and MUC-LHR. The user must select, which flight was affected. After selecting, which flight was with problems, the User must enter for each flight: flight nr. flight date, airline. 2. DISRUPTION DETAILS - at this part, we check for the formal eligibility of the case - see CASE_03, ELIGIBILITY_01, All the questions are from the aformentioned stories. This part determines if the case is eligible. 3. a. IF THE CASE IS NOT ELIGIBLE - Show result to user: "Sorry, but your flight is not eligible for compensation. However you can check the eligility of another flight!" Button to verify another flight "check another flight" - this opens a new, empty form. ELIGIBILITY_01 b. IF THE CASE IS ELIGIBLE - Show result to user: "Congratulations! Your flight is possibly eligible for a compensation up to XXX€" - see ELIGIBILITY_02 Here we ask for the email address (and GDPR checkbox) and show "Next" button. If the user filled out and clicked "next" we create the USER and save the case with status "INCOMPLETE". - CASE_04 and CASE_05 Now we also ask for all passenger details. If the passenger fills them out, we will save the passenger details to this case already created and send the PDF contract CASE_COMPLETED_01 and CASE_COMPLETED_02 With this structure, the progressbar can also be displayed as: 1. Flight details -> 2. Disruption details -> 3. Passenger details (if case is eligible)

## Prios (hidden)
Prio | Description
1 | Must be implemented (Core)
2 | Nice to have
3 | Optional

## Epics
Epic | Description
Case Register | This epic focus on capturing the necessary details (flight details, personal details, type of disruption, reason of disruption).
Case Eligibility Verification | This epic focuses on determing if a case is eligible.
Case Completion and Documentation | This epic involves generating a PDF that contains all case information, and sending it to the customer.
Employee Operations | This epic encompasses the various tasks and operations that can be performed by an employee within the system. It includes functionalities such as case management, data verification, customer communication.
System Administration | This epic includes the various tasks and operations that can be performed by a system administrator within the system. It covers functionalities such as user management and system configuration.
Passenger Operations | This epic includes the various tasks and actions that can be performed by a passenger within the system. It covers functionalities such as submitting cases, documenting cases and communicating with customer support.